## Gantt Chart
2025-2026
| Project Timeline (months) | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
WP | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Commencment of Project
1 | Idea formulation
Task 1.1 Define project scope & aim | bar: 2025-2026 Sep 1
Task 1.2 Find literature sources | bar: 2025-2026 Sep 1 to 2025-2026 Oct 2
Task 1.3 Initial reading about main topic | bar: 2025-2026 Sep 1 to 2025-2026 Oct 2
2 | Literature Review
Task 2.1 Collect related papers & categorize by theme | bar: 2025-2026 Sep 1 to 2025-2026 Nov 3
Task 2.2 Extract theoretical frameworks & summarize findings | bar: 2025-2026 Oct 2 to 2025-2026 Nov 3
Task 2.3 Write section in dissertation | bar: 2025-2026 Oct 2 to 2025-2026 Jan 5
3 | Methodology
Task 3.1 Design experimental framework (CV + statistics pipeline) | bar: 2025-2026 Dec 4 to 2025-2026 Jan 5
Task 3.2 Gather and annotate video data | bar: 2025-2026 Dec 4 to 2025-2026 Jan 5
Task 3.3 Implement homography and detection test scripts | bar: 2025-2026 Jan 5 to 2025-2026 Feb 6
Task 3.4 Define evaluation metrics & validation plan | bar: 2025-2026 Jan 5 to 2025-2026 Feb 6
Task 3.5 Write section in dissertation | bar: 2025-2026 Feb 6 to 2025-2026 Mar 7
4 | Application Development
Task 4.1 Train YOLO detector(s) | bar: 2025-2026 Mar 7
Task 4.2 Integrate video logging & outcome tracking modules | bar: 2025-2026 Mar 7 to 2025-2026 Apr 8
Task 4.3 Perform calibration & bias detection experiments | bar: 2025-2026 Mar 7 to 2025-2026 Apr 8
Task 4.4 Record and organize experiment data for analysis | bar: 2025-2026 Apr 8
5 | Results, Analysis and Discussion
Task 5.1 Conduct statistical analysis of results | bar: 2025-2026 Apr 8 to 2025-2026 May 9
Task 5.2 Interpret results and discuss findings | bar: 2025-2026 May 9 to 2025-2026 Jun 10
Task 5.3 Write section in dissertation | bar: 2025-2026 May 9 to 2025-2026 Jun 10
Project Closure
Notes